When you say “Receive the Mission” (TLP Step 1), in a consulting context, that mission is pulled from the contract / agreement + initial conversations.

Your goal is to extract just enough to issue a WARNO and start planning. Not everything.

!!First impression as a system-builder!!

You are building:

WHO — WHAT — WHERE — WHEN — WHY

### Pull from contract:

- Client name

- Type of service requested

- Location(s)

- Dates / duration

- Purpose of operation

### Output Example:

“Evenfall Advantage conducts a security assessment and operational planning support for [Client] at [Location] from [Dates] to ensure safe and controlled event operations.”

- ☐ Who is the client?

- ☐ What are we being asked to do?

- ☐ Where is it happening?

- ☐ When does it occur?

- ☐ Why does the client want this?

- ☐ What is in scope?

- ☐ What is out of scope?

- ☐ What constraints exist?

- ☐ What resources already exist?

- ☐ Who is in charge?

- ☐ What does success look like?

## MISSION INTAKE FORM (EA-MIF-01)

## 🔒 CLIENT INFORMATION

- Client Company Name: ______________________________

- Primary Point of Contact (POC): _____________________

- POC Phone: ______________________________

- POC Email: ______________________________

## 🎯 MISSION OVERVIEW

- Type of Engagement:

 ☐ Security Assessment

 ☐ Event Security Planning

 ☐ Training

 ☐ Full Operational Support

 ☐ Other: ______________________

- Client Request (in their words):

Mission Statement (to be completed by EA):

## 📍 LOCATION & ENVIRONMENT

- Primary Location(s):

- Venue Type:

 ☐ Bar / Nightclub

 ☐ Festival / Outdoor Event

 ☐ Corporate / Office

 ☐ Private Property

 ☐ Other: ______________________

- Estimated Attendance / Population: __________________

- Environment Notes (urban, rural, indoor/outdoor, etc.):

## 📅 TIMELINE

- Start Date: __________________

- End Date: __________________

- Key Event Dates / Milestones:

- Time Sensitivity:

 ☐ Low

 ☐ Moderate

 ☐ High

 ☐ Immediate

## SCOPE OF WORK

- Services Requested:

- Deliverables Expected:

### 🚫 OUT OF SCOPE (IMPORTANT)

- Items explicitly NOT included:

## ⚙️ CURRENT OPERATIONS (CLIENT CAPABILITY)

- Number of Personnel: __________________

- Leadership Structure:

 ☐ None

 ☐ Informal

 ☐ Defined Chain of Command

- Existing SOPs:

 ☐ Yes

 ☐ No

 ☐ Partial

- Incident Reporting System:

 ☐ Yes

 ☐ No

- Training Level:

 ☐ Minimal

 ☐ Moderate

 ☐ Formalized

## 🛠 RESOURCES AVAILABLE

- Equipment (radios, barriers, etc.):

- Medical Support:

 ☐ None

 ☐ Basic

 ☐ EMS On-site

- Technology / Surveillance:

## ⚠️ RISKS & CONCERNS

- Client-Identified Issues:

- Known or Suspected Risks (EA Assessment):

## ⛔ CONSTRAINTS

- Budget Constraints: __________________

- Staffing Constraints: __________________

- Legal / Licensing Constraints:

- Venue / Operational Restrictions:

## 🧭 COMMAND & CONTROL

- Who has final authority on-site?

- Evenfall Role:

 ☐ Advisory Only

 ☐ Planning & Oversight

 ☐ Operational Control

 ☐ Training Only

## ✅ SUCCESS CRITERIA

- Client Definition of Success:

- Evenfall Definition of Success:

## 📝 INITIAL NOTES (EA USE)